The 65th Meeting of the Baron Courts of Prestoungrange &

Dolphinstoun (1998) Limited by Guarantee held  in The Courts at The Prestoungrange Gothenburg, 229 High Street, Prestonpans on March 1st 2006

Present:	Much Hon. Baron of Prestoungrange [chair]

Annemarie Allan

Sylvia Burgess [Secretary]

Adele Conn

Andrew Crummy

Kristine Cunningham

Chantal Graham

Gillian Hart

Anne Taylor

- Minutes of the 64th Meeting of the Barons Courts [1998]  held on November 20th and December 1st 2005 being a Common Moot with Prestoungrange Arts Festival [2006] held in the Thomas Nelson Suite, The Prestoungrange Gothenburg,  227 High Street, Prestonpans

Agreed:		1.1	That these were a correct record.

- Matters Arising

Transfer of Operations Responsibilities to Prestoungrange Arts Festival 2006 [PAF 2006] Limited by Guarantee

Reported:		2.1[a]	[Minute 05/64/2]	That steady progress was being

made for the transfer and the Arts Directorate for PAF [2006]

had been formally elected on February 27th / 28th , with Andrew

Crummy as Convenor.

2.1[b]	That Sylvia Burgess was assisting in the coming months

as the new enterprise got into its stride both as Company Secretary and Assistant Treasurer.

2.1[c]	That the major activities at PAF [2006] in the coming months were the continuation of Arts Classes and the creation and conduct of the Prestonpans and Cockenzie Arts Festival June 2nd / 9th.

Confirmed:		2.1[a]	That the PAF [2006] Budget for 2006 had been drafted

and was to be tabled at the 4th Meeting of that enterprise in late

March/ early April.

2.1[b]	That with assistance from Gillian Hart some funding to

help promote the Arts Festival in early June had been secured

from Scotland UnLtd, and additional funds were still being

sought.

3.	Continuing & Activities at Barons Courts [1998]

Reported:		3.1	That the major activities to be delivered solo by

Barons Courts [1998] during the transfer of operational

responsibility were as follows:

- The Global Murals Conference August 14th/ 19th

- Totem Pole Carving and Raising

- ‘New’ Battle of Prestonpans Campaign

- University of Gloucestershire Evaluation Study and Template

- Prestonpans History/ Art Treasures books + Calendars

- The Pottery Road Show & Exhibition 2007

- Edinburgh Cow Parade

- RSA Coffee House Challenge

- Poet Laureate

- Prestoungrange ‘Arts Court of Honour’ with ‘Brick Awards’

  - That working with East of Scotland in the

Prestoungrange Gothenburg, to assist in delivering the following:

- Witches’ / Hallowe’en & Pumpkin Contest

- Gothenburg/ Sweden Day July 23rd annually

- Centenary of The Gothenburg in Prestonpans 2008

- John Muir ‘Journey for the Wild’ September 2006

- RLS and Walter Scott celebrations

- Barons’ Day 2006

- Burns’ Week 2007

- Barga Day/ Italian Week 2007

- Totem Pole Carving Painting & Raising

Confirmed:		4.1	That the final stages of carving of the totem pole would

take place at the Prestongrange Museum under canvas at end

March/ early April with storage and painting thereafter at East

Lodge, this to overcome the enduring problems at St Joseph’s

School facilities.

  - That school groups working with Kenny Grieve and

Andrew Crummy, and the National Museums of Scotland, will be finalising designs before the carvers arrive and a display given of the designs at The Prestoungrange Gothenburg.

  - PAF [2006] will receive a contract for painting the

pole finishing not later than May 31st for photographic

purposes.

Reported:		4.1	That Peter Hill of Ratho Iron was preparing the steel

spine for the totem pole’s temporary positioning in August

2006.

5.			University of Gloucestershire Evaluative Study

Reported:		5.1	That Dr Tim Hall was again visiting Prestonpans in

early April to continue interviews and to work with the

Diploma Set, and was planning to create not only a report for

the Global Conference but also a template for global

evaluations by up to 10 other towns prior to the 2008

Conference in Sheffield, Tasmania.

6.			‘New’ Battle of Prestonpans Campaign

Reported:		6.1	That May 16th had been set for the public meeting to

hear Alexander Bennett of National Trust for Scotland outline

the plans being implemented at Culloden with £7.8m of public

funding.

6.2	That the Campaign to create awareness and raise funds

for a major initiative to attract tourists will be synchronised

with the Battle anniversary on September 21st coordinated by Kristine Cunningham, and must and would retain its wholly inclusive approach for all interested parties including artists, biodiversity arboriculturalists, archaeologists and historians.

  - That Gareth Bryn-Jones was preparing an architect’s

impression of the future battle site; the BBC tv documentary on the 45 had been secured; and ClanRanald Highlanders are available for re-enactment scenarios.

6.4	That the East Lothian Courier has requested a full briefing of plans when they are ready.

7.			Future Meetings

Agreed:	7.1	That the Courts will proceed in the coming weeks to conduct their affairs on a project basis for report to the 66th Meeting in late April/ early May.