08/07 Meeting of The Trustees

Wednesday April 25th 2007 @ 6 pm

Court Room @ The Prestoungrange Gothenburg

The Draft Agenda thereat so far is as follows:

Briefing at 6 pm for all Supporters who attend followed by

- Minutes of Meeting 07/07 March 27th 2007 [attached]

- Matters Arising

*

- Progress Report re HLF Funding Applications/ Darren Barker

- Progress Report on RGA Visitor Assessment/ Revenue Study

- Portakabin Exhibition for May/ September - and Volunteers

- Arts Pageant at Prestongrange Kirk June 8th 2007 & Battlefield Tour + subsequent touring of Pageant across Scotland 2007 / 2008

- Design and Implementation of September 21st / 22nd 2007 Events

- Progress Report on Thorntree Stump at National Museum

- Biodiversity Group’s Battle Commemoration & Lion’s Paws

- Website Development and Exploitation

- Establishing The ‘Panel of All Interested Parties’

- Royal Holyrood Palace Sponsor for September 2008 & Re-enactment

- Bing Litter Sweep and Interpretation Restoration

- Encouraging Donations via ‘Classes of Membership/

Subscriptions’ for The Campaign

- All Other Work-in-Progress

- Invitation to 1745 Association

- Any Other Business

18.  Date of 09/07 Meeting @ The Battle Portakabin

6 pm Tuesday June 5th 2007

19. Pageant & RSA Visit: Friday June 8th 2007

*

Trustees wishing to add items to this Agenda please contact Sylvia Burgess, Secretary to the Trustees Ph.  01280 816161

MINUTES of the 07/07 Meeting of The Trustees of the Battle of Prestonpans [1745] Heritage Trust  held in The Court at The Prestoungrange Gothenburg, 227 High Street, Prestonpans on March 27th 2007

Present:	M. Hon Baron of Prestoungrange [in the Chair]

Gareth Bryn-Jones

Kristine Cunningham

Pauline Jaffray

Peter MacKenzie

Lady Prestoungrange

Sylvia Burgess [Secretary]

Apologies:	M. Hon Baron of Dolphinstoun

Garth Morrison

Provost Pat O’Brien

Mathew Wills of Prestoungrange Yr.

- Minutes of 06/07 Meeting of The Trustees held in Barons’ Court, The Prestoungrange Gothenburg, 227 High Street, Prestonpans on February 28th 2007

Confirmed:	1.1	That they were a correct record.

- Matters Arising

There were no matters arising not dealt with elsewhere on the

Agenda.

- Donations & Guarantees by Trustees

Reported:	3.1	That a number of £100 Guarantees from Trustees were

still outstanding and that the Secretary was ensuring their collection.

- Election of Additional Trustee

Agreed:	4.1	To elect Malcolm Scott as an additional Trustee and to

ask the Secretary to ensure that his Guarantee of £100 is

collected.

  - To invite Malcolm Scott to join with fellow Trustees most

especially in exploring the opportunities for hotel investors in consultation with Gareth Bryn-Jones and a new distillery as part of the Battle Heritage development.

- Interim Management Accounts to February 20th 2007

Received:	5.1	The Interim Management Accounts prepared by Mathew

Wills for the Trustees.

Approved:	5.1	The accounts as presented noting that the recent

donation of £100,000 by Malcolm Scott is shown as a debtor of

the Trust and will be drawn upon by agreement as the cash is

required.

Noted:	5.1	That whilst the initial donation of £10,000 from the Tam

O’Shanter Trust was not eligible for tax refunds to the charity,

the private donations by The Baron and Lady of Prestoungrange

and by Malcolm Scott might well qualify and that the Secretary

was currently awaiting formal registration to make such claims

from HMRC.

Agreed:	5.1	That the first call to Malcolm Scott - in respect of the RGA

study - would be made in early April as their invoice becomes

payable.

- Project Planning Grant  [PPG] Application to HLF

Reported:	6.1	That the Draft PPG Form completed by Prince Partners

had been forwarded to HLF in Edinburgh, and an informal

exploratory meeting was scheduled with Colin Maclean shortly

of which the outcome would be reported at the next meeting on

April 25th.

Agreed:	6.1	That Darren Barker’s pro bono work throughout had been

greatly appreciated and that he should be invited to assist the

Trust in following through on its grant applications as may be

appropriate and that to advance this matter he be invited to the

next meeting of the Trustees.

- RGA Visitor Assessment Study

Agreed:	7.1	After discussion amongst extant Trustees and with Malcolm Scott as incoming Trustee separately, that the Trust should now commission the RGA study and to that end Kristine Cunningham and Gordon Prestoungrange should meet with RGA immediately.

  - That RGA should be most especially asked to be mindful

in their assessment of Audience Identification and Assessment/ Visitor Potential of the impact of such analyses on the search for potential hoteliers.

  - That the Secretary should formally contract with RGA and

convene a formal meeting with the RGA study team at Prestonpans at end April/ early May to review progress.

8.		Portakabin Exhibition May/ September 2007

Reported:	8.1	That Kristine Cunningham was pursuing all arrangements

with local Council staff at Meadowmill and applying for Planning

Consents and that a formal opening date of mid May seemed

likely.

  - That the Secretary was ensuring that the Prince’s Battle

flag can fly at all times when the Portakabin Exhibition is open.

  - That Pat O’Brien had made arrangements for the

Interpretation Boards atop the Bing to be restored and the underfoot area.

  - That the AA or RAC would necessarily be asked to install

temporary directional signs for the 2007 Exhibition period until such times as East Lothian Highways can add to the single directional sign presently in place.

8.5	That Margaret O’Connor of ELC was collaborating fully with the project and assisting with possible artefacts.

Agreed:	8.1	That a formal Opening Ceremony in mid-May should be

planned with substantial PR activity as well as continuous

reporting of events in its vicinity.

  - That a roster of Opening Times was vital and would be

considered and agreed at the next meeting.

  - That a budget for exterior and interior interpretation

boards be agreed between the Secretary and Kristine Cunningham with the Murals team from the Arts Festival used as possible.

9.		Arts Pageant: June 8th Prestongrange Kirk

Reported:	9.1	That Andrew Dallmeyer had presented his outline

structure for the Pageant which was well received by all arts

parties, and is now proceeding apace to present the same at its

premiere on June 8th during the Three Harbours Festival,

working with Coreen Scott & The Laverocks,  The Poet Laureate

John Lindsay and the Meanwhile Players led by Malcolm

Watson.

Agreed:	9.1	To continue to seek external grant funding in consultation

with Gillian Hart for the necessary expenses arising and to set

aside a maximum sum of £7,500 for the production as Trust

Grant.

  - That the Pageant should be video recorded if possible

and that a series of presentations across the county/ country scheduled in 2007/ 2008; the first to be hoped for on September 21st / 22nd in Prestonpans.

10.          	Design and Implementation of September 21st/ 22nd Celebrations

Reported:	10.1	That all arrangements are proceeding well with  Hanoverian and Highlanders likely to be available.

Agreed:	10.1	To invite the Minister of Prestongrange Kirk to play the role of Colonel Gardiner on September 21st/ 22nd .

Noted:	10.1	That no progress had yet been made for the hoped for Ball to be formally held in 2008 at the Palace at Holyrood; but that Garth Morrison is seeking to explore this possibility, to also include a royal visit to the battlesite.

11.	Website Development  & Virtual Battle Functions

Reported:	11.1	That Dr Christopher Duffy’s new script, prepared pro

bono on behalf of the 1745 Association’s Council, had now been

posted in lieu of that by Michael of Albany.

  - That discussions had been initiated with Media Logistics

to explore whether a cost effective campaign to elicit Supporters could be launched.

  - That Registrations at the website continued steadily and

all those living in the vicinity of Prestonpans were being invited to a series of scheduled face to face Briefings, now confirmed as:

- April 25th

- July 18th

- September 18th

- October 30th

11.4	That the opportunity to create the ‘virtual’ experience of a

Presentation and Interpretation of the Battle in 1745 was still

being explored by Mathew Wills including the possibility of using

video footage from the 1995 re-enactment.

  - Convening of the  ‘Panel of All Interested Parties’

Reported: 	12.1	That the Minister felt unable to convene the inaugural

meeting due to the impending elections, but had proposed that

Dr Lesley MacInnes of Historic Scotland play a significant role in

the matter since she had accompanied her on her earlier visit to

Prestonpans.

Agreed:	12.1	That early meetings be held with Dr Lesley MacInnes

and with Dr Tony Pollard, who is already working with Historic

Scotland in the matter, so that a clear way forward can be

discerned as soon as possible.

  - That meanwhile the discrete bilateral approaches to

Scottish Power, the Catholic Archdiocese and the ELC at large [but also including its Biodiversity Group/ Rangers] should continue.

  - That the Trustees should consider the possibility of

creating and convening a Conference/ Seminar in association with Biddy Simpson of ELC, Dr Tony Pollard’s Battlefield Archaeology Centre at the University of Glasgow and Queen Margaret University’s Tourism Division early in 2008 to act as a forum and fillip for ‘All Interested Parties’.

  - That the putative presentation of the Trust’s plans at the

ELC’s own in-house seminars in Haddington should be carried forward once the upcoming Councillor elections are concluded.

13.     	Encouraging Classes of Membership and Donations

Agreed:	13.1	That this matter should again be held over for a subsequent meeting.

14.		Works-in-Progress Continuing

Reported:	14.1	That the Litter Sweep under the Keep Scotland Beautiful Banner organised by Stuart Pryde was now firmly scheduled for on April 29th with all Trustees invited to assist.

14.2     That Gareth Bryn-Jones will continue discussions with East Lothian Council to ‘protect the Battlefield and the Routes taken by the two armies’ from encroaching

development and St Joseph’s as a potential hotel with

Malcolm Scott seeking to convene a group of interested

hoteliers.

  - That the Curator in Edinburgh Castle for the original

Thorntree stump remained reluctant for it to be loaned to the Trustees unless most stringent conditions were met but that Gordon Prestoungrange was persisting in attempts to achieve its temporary return.

Agreed:        14.1	That further contact be made with the biodiversity

team which is continuing tree planting to the north of the battlefield and with Biddy Simpson ensuring no Battlefield artefacts are disturbed, to ascertain its current and future plans.

  - That the Riggonhead Defile still needed to be

demarcated and then trodden as part of the September 21st/ 22nd 2007 celebrations.

Reported:	14.4	That nothing further had arisen following suggestions

received for making an audio Walk Guide downloaded from

mobile phones, and the Secretary be asked to follow up.

14.5	That the 1745 Battle Game identified in the USA

from Decision Games is still being evaluated by Dolphinstoun to see whether a competition might be played through.

15.		8th [08/07] Meeting of Trustees: April 25th from 6 pm

Agreed:	15.1 	That the Trustees next meeting will be held on April 25th

2007 at 6 pm at The Prestoungrange Gothenburg.

15.2	That Trustees would continue to hold regular Meetings

throughout the year, with ‘local’ Supporters regularly invited as indicated below with * prior to such meetings; fixed 2007 dates now being:

- *April 25th

- [mid May Opening of Portakabin & Prince’s Battle Flag Raising]

- June 5th   @ THE PORTAKABIN EXHIBITION

- June 8th   ARTS PAGEANT

- *July 18th

- [July 23rd Visit by Lord Mayor of Goteborg]

- *September 18th

- September 21st/ 22nd  RE-ENACTMENT, CEILIDH & CELEBRATION @ HOLYROODHOUSE PALACE

- *October 30th

- November 27th