AIDE  MEMOIRE

Lessons from 2008 Cameo Re-enactments

Once again, as in 2007, it a delight to be able to report that the Trustee and Panners’ consensus was “it worked” well – some said better than in 2007!  We set ourselves very ambitious goals with Edinburgh / Symposium/ extensive Re-enactments but pulled them all off with our ‘distributed responsibilities’ approach vindicated.

The re-enactors had a number of key points to make about how we ‘treat/ optimise’ their contributions that obviously require most deliberate attention as follows:

- Too much walking around diverse sites, on some occasions without an ‘audience’ e.g. the Bing and Waggonway

- No central command for the re-enacting theatricals or pre-planning to share in the design of what the Trust is seeking to achieve.

- Missed out on the encampment option with visitors and kids talking about the weapons and the uniforms etc.

Too much Walking Around was our own design fault. No central command was the re-enactors responsibility – we asked for it and they jibbed at it. Yet it was a pleasure to see how well they worked together as veterans of more than one or two re-enactments. The encampment option was frustrated by multiple no shows and the way out location of Bankton House but has never been seriously addressed by us yet.

Revisiting the 2007 Aide Memoire we can see we actually dealt successfully with almost all points arising then – except the command issue and split locations.

Emerging lessons for September 2009 seem to be:

- Use Cuthill Park as the main focus on Saturday with encampment, BattleGaming perhaps, small skirmishes and the ‘main battle’ clash. It’s ideal terrain for audience and re-enactors and near the town centre. The audience loved the battle scenes, and were not unduly concerned with authenticity. Could run from 11 – 4 + the beach scenes.

- Story telling scripts were once again very well received and remain vital.

- Friday night/ Saturday lunchtime Pipe Band led processions in town and house by house leaflets got the news around.

- ‘Authentic’ Riggonhead Defile Walking @ 5am still a must but needs better managing although Bankton House no longer needed as Cuthill worked so well although the re-enactment of his mortal wounding was much better conducted this time.

- Cameos should be demonstrably ‘staged as such’ e.g. Tranent Churchyard with the Glenbuckets cannon and Clans at Birsley Brae.

- The sea shore scenes as a finale worked well and the Ceilidh was extremely well attended bearing in mind how physically exhausted all must have been except the Czechs.

- The Edinburgh Mercat Cross got the desired early publicity on STV but was otherwise lost from view as HBOS crashed.

- The Gardiner Obelisk needs a major tidying up – it was a mess – as were the Bing Plates and the Signage.

- Parliament was great for morale.