22nd Meeting of the Directors of Prestoungrange Arts

Festival [2006] Limited by Guarantee held on October 21st

2008 in The Barons’ Courts at The Prestoungrange

Gothenburg, Prestonpans

Present:	*Gordon Prestoungrange [in the Chair]

+Andrew Crummy [Arts Convenor]

*Tom Ewing

*Pat Fox

+Gillian Hart [Secretary/Treasurer ]

*June Morgan

*Lynne Schroder

*Avril Wills

Minutes of the 21st Meeting of the Directors held on

September 15th 2008 in the Barons’ Courts at The

Prestoungrange Gothenburg

Agreed:		1.1	That these were a correct record; and the director’s

re-affirmed Gillian Hart to act as a bank signatory under the

usual conditions.

- Belfield Workshops & Car Park Action Plans

Confirmed:	2.1	That the redecoration of the second workshop will be competed in the next two weeks as accommodation available to  Hamish Moore as a contributing member of the Arts Festival on his return from Barga.

Agreed	2.1	That Gillian Hart should ensure co-ordinated action with Andrew Crummy responsible for the exterior design of muralisation to reflect the Belfield Pottery and that Workshop manufactures such as paintings, books, postcards and souvenirs were in progress for the Arts Festivals and the Battle Trust – but that this was certainly not primarily a retail activity and ELC’s enquiry on that issue should be responded to by the Company Secretary.

2.2	That the murals paint store would be in the second workshop and the scaffolding held at East Lodge garage.

Confirmed:	2.2	That the Guide Dispenser @ £1 per issue would be delivered shortly and Pat Fox would supervise installation on the car park close by the totem pole there, with the voucher for use in The Gothenburg also included making it de facto gratis.

  - That plans to create a Pottery Bus Shelter on the car

park and themed refuse bins, along with Entry Signs to the town including notice of its twinning with Barga, will be funded by the Arts Festival charity.

2.4	That the Company Secretary remained in contact with ELC re the rental of the centre Workshop, 14a, and a formal Application has been submitted.

- Grant Applications and Project Funding Action Lines

Reported:		3.1	That Gillian Hart was proceeding with these matters as

agreed and had several projects for which a grant might

be feasible most particularly The 2009 Homecoming series.

Agreed:		3.1	That  the ‘official’ unveiling of the Summerlee Mural

with its final panel should be a planned ceremonial occasion

working with the Poet Laureate and the Burriss and other

Bursary/ Fellowship Award holders in 2008/ 2009, including

Davie Steele music and song and former local inhabitants – in

collaboration as possible with the Community Council and their

campaign for a Miner’s sculpture.

  - That the event might coincide with the Photographic

Mining Exhibition at the Library in February 2009 and the recent contacts with the Heritage Officer at Newbattle Abbey.

Confirmed:	3.1	That Gordon Eadie had created a viable concept for the

‘promenade’ along the Pans coastline for walkers as part of the maintenance and restoration of the sea wall and that Andrew Crummy had been invited to prepare a creative design to generate public interest.

3.2	That designs for the Battle Trust ‘tapestry’ in some 78 panels commemorating the Journey of Prince Charles from Eriskay to Prestonpans in 1745 were also being prepared by Andrew Crummy for a major Spring promotional campaign.

4.			Murals Fest 2009 & Friends of Cuthill Park

Reported:		4.1	That working with The Friends of Cuthill Park much

bolder use will be made of the walls there and greater efforts

made to attract visitors during the Three Harbours Festival

from June 4th – 15th.

4.2	That the cows/ calf/ bull and an additional new cow will

be painted in partnership with local schools and displayed in

the park and one is already with ELIS students.

5.                                Grants in hand from Barons’ Court Charity to PAF [2006]

Noted	:		5.1	That the listing of extant projects with Charity funding

support currently includes:

- 2008/ 9 Burriss Bursary & Other Awards – designs and clear programme still required

- Willie Park Fund re Cuthill Park at RMGC Pt 2. [Gordon Prestoungrange final Pt 2. £2,500]

- Vera Hoban @ Preston Lodge Cross Curricular Grant 2008/ 2009 [£1000 – Gillian Hart] – topic to be notified

- Prestonpans Music Festival [Davie Logan £800 + £1500] – plan awaited

- McGonagall Night II  [ Gillian Hart, John Lindsay & James Brannan] – second night November 26th ‘Oysters’

- Prestoungrange Drama Group initiative: Witch led by Andrew Dallmeyer  [Stuart Cuthbertson/ Kelly Ross/ Coreen Scott]  - scheduled for Hallowe’en

- Gardiner’s Early Life Theatre [Andrew Dallmeyer] – now in progress and premier for The Gathering

- Murals Restoration & Maintenance Programme 2009 [Andrew Crummy & colleagues] including Totem Pole [Tom Ewing] – schedule needed

- Pandores Oyster Shells/ Mosaic [John Lindsay] – schedule awaited

- Mural plaques & website scripts – ongoing but requires firm co-ordination

- Group Tours for The Prestonpans Experience – promotion in hand

- 100 Paintings Art book for Christmas Sale following Goth Centenary/ Minster of Culture’s Exhibition – in hand for early December

6.			Prioritisation of Arts Festival Activities for 2008/ 2009

Confirmed:	6.1	That the ‘arts’ priorities for PAF [2006] across the coming 12 months were as follows:

- Muralisation of Belfield Workshops

- Murals Fest 2009 at Cuthill Park

- Totem Pole maintenance and erection of ELIS Poles

- Support for the ‘nascent’ theatre group

- Town Signage

- Continuing Exhibitions at The Gothenburg

- Battle Tapestry

  - That the ‘business’ priorities for PAF [2006] across the coming 12 months were as follows:

- Schedule of Grant Applications

- Incoming Tours for ‘The Prestonpans Experience’

- Community Right to Buy the Auld Fowler’s HQ and its implications

- Community Right to Buy Auld Fowlers and Listing

Agreed:		7.1      That directors would continue their campaign on all

vectors, reporting progress at the next meeting on November

26th or earlier as required.

  - That sketches envisioning how Auld Fowlers might

look once acquired and developed should be created as soon as Scottish Ministers accepted the community’s application and that these should ‘honour’ the sea as well as Auld Fowlers.

  - That assuming success, a veritable army of community

volunteers will be required to restore and develop it and that their recruitment should be made to coincide with the necessary referendum in EH32 9.

7.4	That the Petition before Holyrood Parliament should be sustained in the ‘national’ interest in respect of local and historical aspects of Listings.

- Forthcoming Meeting of the Directors & The Arts

Directorate

Agreed:		8.1	That the 23rd Meeting of the directors of PAF [2006]

and The Arts Directorate will be held on Wednesday November

26th at 9.30 am.